## Sheet1
Work ??? | Date | Status
CSC 7th result issue solved | 2018-04-02 | Done
CMS_Application working home page | 2018-04-02 | Done
Study CMS Application .. | 2018-04-02 | Done
working on StudentName Update from frontend create sp | 2018-04-03 | Done
Result AcadmicSession Issue | 2018-04-03 | Pending
Result AcadmicSession Issue Solved | 2018-04-04 | Done
Change AcadmicSession in mstAcadsession | 2018-04-05 | Done
working practical internal,Eternal Max in Practicalmst some change in sp | 2018-04-05 | Done
working on DMC Issute Date Some Change in sp | 2018-04-05 | Done
Create DataBase For Result_Application Table Mst | 2018-04-05 | Done
Working with Admin, login sourcecode | 2018-04-06 | Done
Working with student login sourcecode | 2018-04-07 | Done
working testing all update MAU application | 2018-04-07 | Done
working Result Application .. | 2018-04-09 | Done
working MAU App Deploye our system and check all update issue | 2018-04-09 | Done
working Delpoye MAU Application COE Sir System | 2018-04-10 | Done
Working Admin HomePage .. | 2018-04-10 | Pending
Working Admin HomePage .. Search details ,FillGridview | 2018-04-11 | Done
Working Admin HomePage .. Select getone record and save | 2018-04-12 | Done
Working Admin HomePage ..Upload +add new details | 2018-04-13 | Done
Working Admin HomePage .. Add+Save record | 2018-04-14 | Done
working on Admin page Student upload new record with excel | 2018-04-23 | pending
working on Admin page Student upload new record with excel | 2018-04-24 | Done
working on Admin page Student Search Student Record All drop down | 2018-04-25 | Done
working on Admin page Student Search Student Record Student name and regNo | 2018-04-26 | Done
working on Admin page Settings … Search Master view and Add | 2018-04-27 | pending
working on Admin Page General and Examination And User | 2018-04-28 | pending